## Slide 1: SA- Reverse Engineering
Advisor Meeting 10.11.2022
Construction Phase

## Slide 2: Deliverables
Students
  Finish Remote Login Lab
  Finish RE Attempts Lab
  Check out sent Links
  POC for pwntools Lab
  IDA installation Guide
Advisor
  Upload finished Labs to Hacking-Lab

## Slide 3: Decisions from Sprint Meeting
Overview / Quick Guide for Tools used in all Labs
Make additional Notes on guided tests
No CICD  Not necessary
All Categories, Level and Modes to better specify the Labs

## Slide 4: Labs Updated
Updated Labs based on Feedback
Updated RE Attempts Lab
  Edited Files
Updated Remote Login Lab
  More Pictures as guide
  Changed Mode
  Added docker-compose
  Fixed Markdown problems

## Slide 5: Pwntools Lab
Walkthrough
Find Vulnerability  Exploit it with pwntools
Local or Remote
Idea: First Introduction to pwntools, next labs won’t be as guided

## Slide 6: Plan for Labs
Topic | Description
(Refresher) | Refreshing Knowledge of previous modules and lectures
Introduction into RE #1 | Introducing the different tools to the student
Introduction into RE #2 | Static analysis of a given Program
Introduction into RE #3 | Dynamic analysis of a given Program
First RE attempts | Given simple files compiled in several languages (py, c#, c++…) get flag
Client Server Application | Using Docker to give students a downloadable file with changing flag
Pwntools | Find Vulnerability and exploit with pwntools
First keygen | Not only finding out the password but writing a keygen for the program
Harder CrackMes | Introduce new native API funcs / techniques like stack strings
Injection techniques | Explain some injection techniques
Dump memory | Explain how to dump memory off a given executable which uses a previously explained injection technique
“Anti”- Techniques | Introduce “Anti”- Techniques and provide program for students to bypass